# PCC Gardens Manager

Implementation Plan — Porirua City Council

Prepared: June 2026

## Phase 0: Final In-House Testing  (This Week)

- Complete internal testing across both the web app and mobile app

- Verify production data accuracy — assets, teams, scheduled jobs

- Fix any critical bugs before handing over to the client

- Confirm all manager, supervisor and crew roles behave correctly

Gate: No critical bugs open; production data verified complete

## Phase 1: Manager Acceptance Testing  (Week 2)

Who: 1-2 managers (e.g. Daniela + one other)

### What to test — Web App

- Asset browsing, filtering, and detail views

- Viewing and editing scheduled jobs

- Running and reviewing audits

- Team assignment views

### What to test — Mobile App

- Logging in on their own device

- Asset detail and Start Audit flow

- Photo capture on audits

- Job views

### Actions

- Set up a short walk-through session (30-45 min) to demonstrate key workflows

- Give managers a simple feedback form or shared doc to log issues

- Target 3-5 business days of testing, then hold a debrief

Gate: Managers sign off on core workflows; any blockers resolved

## Phase 2: Supervisor Pilot  (Week 3)

Who: 1-2 supervisors added to the system

### Focus

- Supervisors review their crew's weekly job schedule

- Check asset details and boundaries for their sites

- Familiarise with the mobile app before their crew uses it

### Actions

- Brief onboarding session (15-20 min, can be done remotely)

- Check that job and schedule refresh workflows are intuitive for field use

Gate: Supervisors comfortable navigating the system independently

## Phase 3: Single Crew Field Pilot  (Weeks 4-5)

Who: 1 crew (2-4 people) — pick the most tech-comfortable crew

Critical safety rule: Continue running existing paper/spreadsheet processes in parallel for this crew during the pilot.

### Focus

- Crew uses the mobile app for daily job views

- Supervisor runs audits via the Start Audit button

- Job completion and audit data captured in the new system

### Actions

- 15-minute on-site device setup session per crew member

- Daily check-in for the first week (5-minute call or message)

- Track any data gaps or usability issues

Gate: Pilot crew completing jobs and audits reliably; no data loss observed

## Phase 4: Full Field Rollout  (Weeks 6-7)

Who: All remaining crews, phased team by team — not all at once

### Actions

- Roll out 1-2 teams per day to avoid overwhelming support

- Keep spreadsheet backup live for 2 weeks after the last team is onboarded

- Designate one internal point-of-contact for field staff questions

Gate: All crews active; parallel process formally retired

## Ongoing (Post-Rollout)

- Weekly check-in for the first month to catch recurring issues

- Identify a "power user" supervisor or manager as internal champion

- Plan a 6-week structured review to gather feedback

## Key Risk Controls

| Risk | Mitigation |
| --- | --- |
| Data missing or wrong | Verify all assets and teams before Phase 1 |
| Device compatibility issues | Test on actual crew devices in Phase 2 |
| Field crew resistance | Pick a willing, tech-comfortable crew for the pilot |
| System outage mid-rollout | Keep paper process live until Phase 4 gate is met |
| Photos/audits not saving | Check GCS storage in production before Phase 3 |

Principle: Never fully retire the old process until the new one has proven itself with a real crew for at least two weeks. That way there is always a safe fallback without any risk of data loss.